Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 30 August 2026 |
| --- | --- |
| Team ID |  |
| Project Name | An employee requests installation of licensed software through the Service Catalog |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Service Catalog | USN-1 | As an employee, I want to access a Software Installation Request catalog item so that I can request licensed software through the Service Catalog. | 3 | High |
| Sprint-1 | Request Form | USN-2 | As an employee, I want to enter Software Name, Version Required, License Justification and Urgency so that I can provide the required information. | 3 | High |
| Sprint-1 | Request Submission | USN-3 | As an employee, I want to submit my software installation request and receive a request/item number so that I can track it. | 2 | High |
| Sprint-1 | Request Validation | USN-4 | As an employee, I want to verify my submitted request through the Service Portal so that I know the request was successfully created. | 2 | Medium |
| Sprint-2 | Approval Workflow | USN-5 | As an approver, I want to review and approve or reject software installation requests so that only authorized requests are fulfilled. | 3 | High |
| Sprint-2 | Task Automation | USN-6 | As an IT fulfiller, I want a catalog task to be automatically created after approval so that I can perform the software installation. | 3 | High |
| Sprint-2 | Task Assignment | USN-7 | As an IT fulfiller, I want the catalog task to be assigned to the Software Support team so that the correct team can handle the request. | 2 | High |
| Sprint-2 | Request Tracking | USN-8 | As an employee, I want to track the status of my software request so that I know its current progress. | 2 | Medium |
| Sprint-3 | Exception Handling | USN-9 | As a ServiceNow administrator, I want an Incident to be created automatically when a software request is placed On Hold because of a license shortage. | 3 | High |
| Sprint-3 | Business Rule | USN-10 | As an administrator, I want a Business Rule to detect the On Hold state and create the appropriate Incident record. | 3 | High |
| Sprint-3 | Task Status | USN-11 | As an IT fulfiller, I want to update the catalog task state from Open to Work in Progress and Completed so that fulfillment progress is recorded. | 2 | Medium |
| Sprint-3 | Notifications | USN-12 | As an employee, I want to receive relevant request/status notifications so that I remain informed about the installation process. | 2 | Medium |
| Sprint-4 | Testing | USN-13 | As an administrator, I want to test the complete request, approval, task and exception flow so that the system works correctly. | 3 | High |
| Sprint-4 | Update Set | USN-14 | As an administrator, I want to capture the project configurations in an Update Set so that the solution can be transferred to another instance. | 3 | High |
| Sprint-4 | Deployment | USN-15 | As an administrator, I want to export and import the Update Set so that the configured solution can be deployed to another ServiceNow instance. | 2 | Medium |
| Sprint-4 | Final Validation | USN-16 | As an administrator, I want to validate all migrated components so that no configuration or functionality is missing. | 2 | High |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 6 Days | 03 Aug 2026 | 08 Aug 2026 | 10 | 08 Aug 2026 |
| Sprint-2 | 10 | 6 Days | 10 Aug 2026 | 15 Aug 2026 | 10 | 15 Aug 2026 |
| Sprint-3 | 10 | 6 Days | 17 Aug 2026 | 22 Aug 2026 | 10 | 22 Aug 2026 |
| Sprint-4 | 10 | 6 Days | 24 Aug 2026 | 29 Aug 2026 | 10 | 29 Aug 2026 |

# Velocity

Velocity represents the amount of work completed by the team during a sprint.

For this project:

Total Story Points = 40

Number of Sprints = 4

### Average Velocity

Average Velocity = Total Completed Story Points / Number of Sprints

Average Velocity = 40 / 4 = 10 story points per sprint

Therefore, the planned team velocity for this project is:

### Average Velocity = 10 Story Points/Sprint

For a 6-day sprint:

Velocity per day = 10 / 6 = 1.67 story points/day

Burndown Chart:

| Day | Date | Remaining Work (Ideal) | Remaining Work (Actual) |
| --- | --- | --- | --- |
| Day 0 (Start) | 03 Aug 2026 | 10 Points | 10 Points |
| Day 1 | 04 Aug 2026 | 8.3 Points | 10 Points |
| Day 2 | 05 Aug 2026 | 6.7 Points | 8 Points |
| Day 3 | 06 Aug 2026 | 5.0 Points | 5 Points |
| Day 4 | 07 Aug 2026 | 3.3 Points | 5 Points |
| Day 5 | 08 Aug 2026 | 1.7 Points | 2 Points |
| Day 6 (End) | 08 Aug 2026 | 0 Points | 0 Points |